## Backlog
Note: We have added some extra columns for the convenience of development. The original column titles in the template are highlighted in bold black, and the extra columns are in purple. Column Definitions: 1) MVP (Minimum Viable Product): the smallest set of core features that delivers usable user value and validates product direction. 2) Iteration (Sprint) Number: the sprint in which the user story is planned. 3) Estimation (Story Points): a relative measure of implementation effort and complexity, including uncertainty, dependencies, and testing effort.
Story ID | User Role | Scope | Story Name | Description (User Story) | Priority | Iteration (Sprint) number | Estimation (Story Points) | Dependency | MVP | Acceptance Criteria | Notes | Date started (planned) | Date finished (planned)
MB-01 | TA/MO/Admin | Auth | Secure Login | As a system user, I want to log in securely, so that I can access my role-specific functions. | High | 1 | 3 | - | Yes | 1) Users can log in with identifier + password. 2) Invalid credentials show an error message. 3) Successful login redirects to the correct role workspace. | Iteration 1 core (First assessment) | 2026-03-22 | 2026-03-29
MB-02 | TA/MO | Auth | Role Selection | As a user, I want to choose my role before login, so that I can enter the correct workflow. | High | 1 | 2 | MB-01 | Yes | 1) TA/MO role entry is visible. 2) Selected role state is applied in login flow. 3) Incorrect role path is blocked by front-end validation. | Iteration 1 core (First assessment) | 2026-03-22 | 2026-03-29
MB-03 | TA | Auth/Profile | TA Registration with Auto ID | As a TA, I want to register with an auto-generated TA ID, so that I can start quickly. | High | 1 | 3 | MB-02 | Yes | 1) TA ID is auto-generated on registration. 2) Form validation is required before submit. 3) Registration data is persisted in text-based storage. | Iteration 1 core (First assessment) | 2026-03-22 | 2026-03-29
MB-04 | TA | Profile | Profile Create/Edit | As a TA, I want to create and edit my profile, so that MO can evaluate my qualifications. | High | 1 | 3 | MB-03 | Yes | 1) Profile form supports core info and skills. 2) Saved data is reloaded on revisit. 3) Updates correctly overwrite old values. | Iteration 1 core (First assessment) | 2026-03-22 | 2026-03-29
MB-05 | TA | Profile | CV Upload | As a TA, I want to upload my CV, so that I can apply for positions. | High | 1 | 3 | MB-04 | Yes | 1) CV upload supports file validation. 2) Storage layer saves file path and metadata. 3) MO can open the uploaded CV. | Iteration 1 core (First assessment) | 2026-03-22 | 2026-03-29
MB-06 | TA | Jobs | Browse/Search Jobs | As a TA, I want to browse and search available jobs, so that I can find suitable opportunities efficiently. | High | 1 | 3 | MB-01 | Yes | 1) Job list is displayed from local data. 2) Keyword search filters the list. 3) Empty-state messaging is shown when no jobs exist. | Iteration 1 core (First assessment) | 2026-03-22 | 2026-03-29
MB-07 | TA | Jobs | Job Detail View | As a TA, I want to view job details before applying, so that I can make informed decisions. | High | 1 | 2 | MB-06 | Yes | 1) Job details can be opened from job list. 2) Details include requirements and schedule/location. 3) Detail view is linked to apply action context. | Iteration 1 core (First assessment) | 2026-03-22 | 2026-03-29
MB-08 | TA | Application | One-Click Apply | As a TA, I want to apply in one clear action, so that my application is recorded immediately. | High | 2 | 5 | MB-05, MB-07 | No | 1) Apply action creates a new application record. 2) Duplicate applications are prevented or warned. 3) New record appears in status tracking. | Iteration 2 target (Intermediate) | 2026-04-05 | 2026-04-12
MB-09 | TA | Application | Status Timeline | As a TA, I want a timeline for application status, so that I always know progress. | High | 1-2 | 3 | MB-08 | Yes | 1) Application status can be queried by TA ID. 2) Each item shows current status and update time. 3) Step history can be expanded/viewed. | Cross-iteration delivery (1->2) | 2026-03-22 | 2026-04-12
MB-10 | TA | Application | Status Summary/Notifications | As a TA, I want summary counts and notifications, so that I can monitor all applications quickly. | High | 1-2 | 2 | MB-09 | Yes | 1) Summary counters are visible. 2) Notification panel shows pending actions. 3) Neutral empty state is shown when no reminders exist. | Cross-iteration delivery (1->2) | 2026-03-22 | 2026-04-12
MB-11 | MO | Auth | MO Secure Login | As a MO, I want to log in securely, so that I can manage recruitment tasks. | High | 1 | 2 | MB-01 | Yes | 1) MO credentials are validated. 2) Login failures show clear messages. 3) Successful login opens MO workspace. | Iteration 1 core (First assessment) | 2026-03-22 | 2026-03-29
MB-12 | MO | Jobs | Post TA Jobs | As a MO, I want to post TA jobs with requirements, so that students can apply to suitable roles. | High | 1-2 | 3 | MB-11 | Yes | 1) Posting form includes module and skills requirements. 2) Saved jobs appear in TA-visible list. 3) Job edits are persisted. | Cross-iteration delivery (1->2) | 2026-03-22 | 2026-04-12
MB-13 | MO | Application | View Applicants by Job | As a MO, I want to view applicants per job, so that I can compare candidates. | High | 2 | 3 | MB-12, MB-08 | No | 1) Applicants are listed by job. 2) Profile and CV can be opened per applicant. 3) Basic filtering/sorting is available. | Iteration 2 target (Intermediate) | 2026-04-05 | 2026-04-12
MB-14 | MO | Application | Select Applicants | As a MO, I want to select suitable applicants and publish results, so that decisions are finalized and visible to TA. | High | 2 | 5 | MB-13 | No | 1) MO can mark accepted/rejected candidates. 2) Decisions are persisted. 3) TA status view reflects decision updates. | Iteration 2 target (Intermediate) | 2026-04-05 | 2026-04-12
MB-15 | Admin | Admin | Workload Check | As an admin, I want to review TA workload, so that I can avoid over-allocation. | Medium | 3 | 3 | MB-14 | No | 1) Admin panel shows TA workload metrics. 2) Potentially overloaded TAs are identifiable. 3) Data can be viewed by role/job dimension. | Iteration 3 target | 2026-04-19 | 2026-04-26
MB-16 | Admin | Admin | Applicant Record Management | As an admin, I want to manage applicant records, so that data remains accurate and organized. | Medium | 3 | 3 | MB-13 | No | 1) Admin can search applicant records. 2) Incorrect fields can be updated. 3) Changes are persisted and traceable. | Iteration 3 target | 2026-04-19 | 2026-04-26
MB-17 | TA | Intelligence | Missing Skills Feedback | As a TA, I want feedback on missing skills, so that I can improve future applications. | Low | 4 | 5 | MB-04, MB-12 | No | 1) System compares TA skills with job requirements. 2) Missing skills list is generated. 3) Feedback is clearly presented. | Iteration 4 target | 2026-05-03 | 2026-05-10
MB-18 | MO | Intelligence | Candidate Matching Support | As a MO, I want system-generated candidate matching, so that I can decide faster. | Low | 4 | 8 | MB-13 | No | 1) Matching score is generated per candidate. 2) Candidate list is ranked by score. 3) Key matching factors are shown. | Iteration 4 target | 2026-05-03 | 2026-05-10
MB-19 | Admin | Intelligence/Admin | Workload Warning Alerts | As an admin, I want workload warnings, so that I can balance assignments fairly. | Low | 4 | 3 | MB-15 | No | 1) Overload threshold is configurable. 2) Warning appears when threshold is exceeded. 3) Risk is visible before final assignment confirmation. | Iteration 4 target | 2026-05-03 | 2026-05-10
MB-20 | TA | Profile | Settings Center | As a TA, I want one place for profile/security/preferences, so that account maintenance is simple. | High | 1 | 3 | MB-04 | Yes | 1) Settings center includes tabbed sections. 2) Explicit save is required after edits. 3) Saved/unsaved states are clearly indicated. | Iteration 1 core (First assessment) | 2026-03-22 | 2026-03-29
MB-21 | TA | Profile | Avatar Upload/Crop | As a TA, I want to upload and crop my avatar, so that my profile appears complete and professional. | High | 1 | 3 | MB-20 | Yes | 1) File type and size validation is enforced. 2) Crop flow is supported before upload. 3) Final avatar is stored and rendered reliably. | Iteration 1 core (First assessment) | 2026-03-22 | 2026-03-29
MB-22 | TA | Security | Password Change | As a TA, I want to change my password securely, so that my account remains protected. | High | 1 | 3 | MB-01 | Yes | 1) Current password and new password rules are validated. 2) Weak/reused passwords are rejected. 3) New salt/hash is persisted successfully. | Iteration 1 core (First assessment) | 2026-03-22 | 2026-03-29
MB-23 | TA | Intelligence | Explainable Recommendations | As a TA, I want recommendations with reasons, so that I can trust and act on suggestions. | Medium | 2 | 5 | MB-06, MB-04 | No | 1) Recommended jobs are ranked by score. 2) Each recommendation includes explanation factors. 3) Recalculation works after profile updates. | Iteration 2 target (Intermediate) | 2026-04-05 | 2026-04-12
MB-24 | TA | Intelligence | Availability Matching | As a TA, I want to record availability and avoid schedule conflicts, so that I apply only to feasible jobs. | High | 2 | 5 | MB-08, MB-06 | No | 1) Availability editor is provided. 2) Apply flow checks schedule conflicts. 3) Conflicts trigger clear warning messages. | Iteration 2 target (Intermediate) | 2026-04-05 | 2026-04-12
MB-25 | TA/MO/Admin | Security | Session Access Control | As a user, I want protected routes to require valid session, so that unauthorized access is blocked. | High | 2 | 5 | MB-01 | No | 1) Protected routes require session validation. 2) Unauthenticated requests are redirected or return 401. 3) Role-based access boundaries are enforced. | Iteration 2 target (Intermediate) | 2026-04-05 | 2026-04-12
MB-26 | TA/MO/Admin | Security | Brute-Force Lockout | As a platform owner, I want lockout for repeated failed logins, so that accounts are safer from abuse. | High | 2 | 3 | MB-01 | No | 1) Failed-attempt threshold triggers temporary lockout. 2) UI shows lockout and retry guidance. 3) Lockout metadata is persisted. | Iteration 2 target (Intermediate) | 2026-04-05 | 2026-04-12
MB-27 | TA | UX | Mobile-Friendly Experience | As a TA, I want mobile-friendly pages, so that I can check jobs and status on phone/tablet. | Medium | 2 | 3 | MB-06, MB-09 | No | 1) Core pages are usable on narrow screens. 2) Primary actions support touch interaction. 3) Typography and spacing remain readable on mobile. | Iteration 2 target (Intermediate) | 2026-04-05 | 2026-04-12
MB-28 | TA | Analytics | Recruitment Dashboard | As a TA, I want analytics charts for applications and outcomes, so that I can understand progress over time. | Medium | 3 | 5 | MB-09, MB-10 | No | 1) Dashboard shows key metrics and trends. 2) Time-range filtering is available. 3) Empty data states are handled with clear guidance. | Iteration 3 target | 2026-04-19 | 2026-04-26
MB-29 | TA/MO | Storage | CV Path-Based Storage Compliance | As a MO, I want uploaded CV files stored with text-based relative paths, so that the system stays compliant with text-file storage constraints while preserving original PDF formatting. | High | 1 | 3 | MB-05 | Yes | 1) CV files are saved in a controlled folder. 2) Text metadata stores relative file paths for each CV. 3) MO can open original CV files from stored paths. | Iteration 1 core (First assessment) | 2026-03-22 | 2026-03-29
MB-30 | TA | Application | MO Review Progress Visibility | As a TA, I want to see MO review progress stages, so that I can track what is happening after submission. | High | 1-2 | 3 | MB-09 | Yes | 1) Status stages include at least Submitted, In Review, Interview, and Final Decision. 2) Each stage change records an update timestamp. 3) TA timeline clearly shows current stage and recent transition. | Cross-iteration delivery (1->2) | 2026-03-22 | 2026-04-12
MB-31 | Admin | Security/Admin | Highest-Privilege Admin Access Control | As an admin, I want highest-level permission boundaries with controlled role actions, so that governance is clear and unauthorized operations are prevented. | High | 2-3 | 5 | MB-25 | No | 1) Role permissions are explicitly defined for TA, MO, and Admin. 2) Admin-only operations are protected from TA/MO access. 3) Unauthorized role actions return clear denial responses. | Cross-iteration delivery (2->3) | 2026-04-05 | 2026-04-26
MB-32 | TA | Application | Withdraw Application | As a TA, I want to withdraw an application before final decision, so that I can correct mistakes or change plans. | Medium | 2 | 3 | MB-08 | No | 1) TA can withdraw only non-final applications. 2) Status changes to Withdrawn with timestamp. 3) MO view updates immediately. | Iteration 2 target (Intermediate) | 2026-04-05 | 2026-04-12
MB-33 | MO | Jobs | Job Closing Control | As a MO, I want to close a job posting, so that no further applications are accepted after deadline or quota. | High | 2 | 3 | MB-12 | Yes | 1) MO can set Open/Closed state. 2) Closed jobs block new applications. 3) TA side clearly shows closed status. | Iteration 2 target (Intermediate) | 2026-04-05 | 2026-04-12
MB-34 | TA/MO | Notification | Decision Notification | As a TA, I want to receive a notification when MO updates my result, so that I do not need to check manually. | High | 2 | 3 | MB-14 | Yes | 1) Status change triggers in-app notification. 2) Notification contains job and decision summary. 3) Read/unread state is supported. | Iteration 2 target (Intermediate) | 2026-04-05 | 2026-04-12
MB-35 | MO | Application | Applicant Shortlist | As a MO, I want to shortlist candidates before final decision, so that I can manage review in stages. | Medium | 2 | 5 | MB-13 | No | 1) MO can mark shortlisted applicants. 2) Shortlist filter is available in applicant list. 3) Shortlisted state is persisted. | Iteration 2 target (Intermediate) | 2026-04-05 | 2026-04-12
MB-36 | Admin | Audit | Action Audit Log | As an admin, I want an audit trail of key actions, so that disputes and mistakes can be traced. | High | 3 | 5 | MB-25 | No | 1) Key actions (post/apply/select/update) are logged. 2) Log includes actor, time, action, target. 3) Admin can query logs by role/time. | Iteration 3 target | 2026-04-19 | 2026-04-26
MB-37 | TA | Profile | Mandatory Completion Gate | As a TA, I want clear mandatory profile checks, so that I know what to complete before applying. | High | 1 | 2 | MB-04 | Yes | 1) Required fields are marked explicitly. 2) Apply button is disabled until mandatory data is complete. 3) Missing fields are listed to user. | Iteration 1 core (First assessment) | 2026-03-22 | 2026-03-29
MB-38 | MO/Admin | Data | CSV Export for Reports | As a MO/Admin, I want to export applicants and decisions to CSV, so that reporting is easier. | Medium | 3 | 3 | MB-13, MB-14 | No | 1) Export includes selected filter range. 2) CSV has consistent headers and encoding. 3) Export file is downloadable and readable in Excel. | Iteration 3 target | 2026-04-19 | 2026-04-26
MB-39 | TA/MO/Admin | Security | Password Reset (Admin-assisted) | As a user, I want a secure reset process when password is forgotten, so that account recovery is possible. | Medium | 3 | 5 | MB-22 | No | 1) Reset request is recorded and verified by role policy. 2) Temporary reset token/code has expiry. 3) Reset success invalidates old credentials. | Iteration 3 target | 2026-04-19 | 2026-04-26
MB-40 | TA | UX | Application Draft Save | As a TA, I want to save a draft before final submit, so that I can finish application details later. | Low | 3 | 3 | MB-08 | No | 1) TA can save and reopen draft applications. 2) Drafts are not visible to MO until submit. 3) Submit converts draft to official application record. | Iteration 3 target | 2026-04-19 | 2026-04-26
MB-41 | TA/MO | Reliability | Concurrent Update Protection | As a user, I want the system to prevent accidental overwrite when data was changed by others, so that records stay consistent. | Medium | 3 | 5 | MB-12, MB-13 | No | 1) Update checks version/timestamp. 2) Conflict returns clear message. 3) User can reload and retry safely. | Iteration 3 target | 2026-04-19 | 2026-04-26